Commissioning Sequence Progress Check Sheet

System: Elevators

Overview: Work may consist of modernization or replacement of existing elevators, or installation of new elevators. Covers both types of elevators – hydraulic type and electric traction type.

Specification Section:  __________     Elevator Type & No._______________

Acknowledgments

Owner		Contractor

_____          _____        Shop Drawings Submitted (To A/E)

_____          _____        Print Review Completed (by UM Elevator Dept.)

_____          _____        Shop Drawings Approved

_____          _____        Notification / Salvage Completed (Demo of Existing

Elevator(s) – Contact UM Elevator Dept. (747-3246)

_____          _____        Telephone Order Placed (1 or 2 lines per elevator)

_____          _____        O&M Manual (Draft) Submitted and approved

_____          _____        Field Review Completed (by UM Elevator Dept. prior

to installation)

_____          _____        Major Components Delivered

_____          _____        Jack Inspection Completed (for Hydraulic type) by UM

Elevator Dept.

_____          _____        Electrical Complete

_____          _____        Adjusting Performed

_____		    _____		Issues from Adjusting Resolved

_____          _____        Installation Complete

_____          _____        Final Adjusting Completed (UM Elevator Dept. attends)

_____          _____        Code Inspection Complete (State of Michigan Elevator

Inspector), Report Submitted to Owner

_____          _____        Mfgr's Performance Testing Completed (Running Speed

Test with Full Design Load)

_____          _____        Elevator Accepted by UM Elevator Dept.

_____		    _____		O & M Manual (Final) Submitted

_____		    _____		All Punch-list Items Completed

_____          _____        Operator Training/Instruction Scheduled and Completed

_____		    _____		System Accepted by Owner