## [Insert CM Firm’s Logo Here]

University of Michigan

Name of Project

UM Project No. P0000xxxx

Construction Manager’s Quarterly Construction Summary

Construction Manager: [Name]

Architect: [Name]

PROGRESS OVERVIEW

- Summarize the general progress in narrative form.

CRITICAL ISSUES

- List schedule or budget issues and detail how issues are being addressed. Or, indicate "None at this time."

[At the start of the project, insert the A/E's rendering here and provide photo credit. Once there has been significant construction progress, the rendering may be replaced with a site progress photo. If possible, use the same perspective as the A/E rendering.]

# SAFETY

1) Description of CM firm’s safety mission statement/motto.

2) Insert image of U-M safety report from the last month of the reporting quarter. Do not include any other charts or graphs.

See Appendix A for additional Safety Report pages

DIVERSITY BUSINESS PARTICIPATION

| Trade Name | Contract Amount |
| --- | --- |
| If no awards, indicate "Nothing to report at this time." | $ |

# SCHEDULE OVERVIEW

Do not provide a bar chart or other graphic.

Construction is [%] Complete through [Date/Month].

| Bid Document Release Dates from Design Professional to CM per the CM SOPD |  |  |  |  | Out to Bid |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Bid Package No. | Description | Original Schedule per SOPD | Current Schedule | Actual |  | Original Schedule | Current Schedule | Actual |
| DR #0 | Demo and Abatement | 8/23/19 | 8/2/19 | 8/2/19 |  | 8/5/19 | 8/5/19 | 8/5/19 |
| DR #1 | Precast Concrete design-assist & installation | 7/8/19 | 7/8/19 | 7/8/19 |  | 6/28/19 | 7/16/19 | 7/16/19 |
| DR #2 | Earth Retention Systems | 9/24/19 | 9/24/19 | 9/24/19 |  | 10/22/19 | 10/2/19 | 10/26/19 |

# MILESTONES

List milestones listed in CM SOPD and any other milestones determined by the Project Team at the beginning of the project.

| Description | Original Schedule per SOPD | Current Schedule | Actual |
| --- | --- | --- | --- |
| Start of Demolition | 9/23/19 | 9/23/19 | 9/23/19 |
| Start of Precast Concrete | 3/17/20 | 3/17/20 | TBD |
| Building Enclosure | 11/22/20 | 11/22/20 | TBD |

3-MONTH OUTLOOK

| Month/Year | Month/Year | Month/Year |
| --- | --- | --- |
| - Continue precast concrete fabrication - Begin precast installation - Complete concrete foundations and walls - Continue earthmoving operations and backfilling | - Continue precast concrete fabrication - Begin precast installation - Complete Madison Street water line install - Begin masonry installation | - Continue precast concrete - Begin basement underground piping installation - Begin window installation - Begin layout of basement walls |

ADDITIONAL MEASURABLES (reported in business days)

If review time exceeds goal, provide an explanation.

| RFI Review: | Submittal Review: | Change Management: | Pay Applications: |
| --- | --- | --- | --- |
| Total RFI’s: | Total Submittal Packages: | Total No. of CCDs: | Total Pay Apps: |
| Avg. Review Time: | Avg. Review Time: | Avg. CCD to CO: | Avg. Payment Time to CM: |
| Review Time Goal: | Review Time Goal: | Goal for CCD to CO: | Payment Goal U-M to CM: |
|  |  |  | Avg. CM Payment to Trade: |
|  |  |  | Payment Goal CM to Trade: |

Budget/Cost Status: Invoice Summary

Insert the invoice summary from the last month of the reporting quarter.

Construction Cash Flow

If the actual varies significantly from the projection, provide an explanation.

# SUSTAINABILITY & ENVIRONMENT

Narrative of CM’s Sustainability and Environmental program.

# PROGRESS PHOTOGRAPHS

Insert photos and include dates taken and brief description.

| Concrete footing installation | Foundations looking southwest |
| --- | --- |
| Foundations looking south | Complete foundations backfilled |

Appendix A